## ProductBacklog
PRODUCT BACKLOG
Batch 2018_2019
SPRINT BACKLOG | US ID | BACKLOG ITEM |  |  | PRIORITY | RESPONSIBLE | ESTIMATE DATE | REMARKS
|  | AS A/AN | I WANT TO | SO THAT
1
1 | SB1/US1 | Developer | take input from microphone | I can use this for trainig purposes. | 1
1 | SB1/US2 | Developer | classify the voices | I can recognize the voice of human | 1
1 | SB1/US3 | Developer | filter the voice of human | I can reduce the noise | 1
1 | SB1/US4 | Developer | classify the voice of male and female. | I can easily train the data accordingly | 1
1 | SB1/US5 | Developer | reduce the noise and perform data cleaning. | I can get the best result. | 1
1 | SB1/US6 | Developer | train my system with different algorithm | I can calculate the efficency and select the best model. | 1
1 | SB1/US7 | Developer | apply the recognition algorithm. | I can get the output as text | 1
1 | SB1/US8 | Developer | convert the text input to speech. | machine can reply the anser accordingly as voice. | 1
1 | SB1/US9 | Developer | merge the speech to text and text to speech. | I can use it in my Application. | 1
3 | SB3/US1 | Developer | Build the database. | I can save information of user in it | 3
3 | SB3/US2 | Developer | build the GUI of application | It is more user friendly | 3
3 | SB3/US3 | Developer | add some features | User can to Control my device through Assistant. | 3
3 | SB3/US4 | Developer | add some web features | User get all the information from various resourses in a single screen. | 3
3 | SB3/US5 | Developer | Build the application more adaptive | It can adapt itself according to user needs. | 3
3 | SB3/US6 | User | Control other things with it | It can save users time and energy. | 3
3 | SB3/US7 | Developer | intregate all Modules of project | It can run smoothely. | 3
3 | SB2/US1 | Developer | collect all the data from different converstations | use them in my project as training data. | 2
2 | SB2/US2 | Developer | filter and collect the data | I can use it in my project. | 2
2 | SB2/US3 | Developer | test different models | I can get the sentiment of the input. | 2
2 | SB2/US4 | Developer | test different models | I can get the perfect output for the input. | 2
2 | SB2/US5 | Developer | Select some best models. | I can use all of them in my chatbot | 2
2 | SB2/US6 | Developer | calculate the confidence of different output from different model | I can get the best output | 2
2 | SB2/US7 | Developer | make a adaptive algorithm | chatbot can learn more through user past chat. | 2
2 | SB2/US8 | Developer | get interest of the user. | I can make it more user friendly | 2
2 | SB2/US9 | User | chatbot for getting Important reminders and information. | I can get the best out of it | 2
4 | SB4/US1 | Developer | optimize my application | It work fast | 4
4 | SB4/US2 | Developer | Implement my software on any platform | I can get the live experience of it | 4
4 | SB4/US3 | Developer | test It again | It doesnot give any errors in future | 4
4 | SB4/US4 | Developer | devlop it for different platform and connect it with different applications | It run indifferent environment. | 4

## SprintBacklog 1
SPRINT BACKLOG 1
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 1 - <SPEECH RECOGNITION>
SB1/US1 | As a devloper I want to take input from microphone so that I can use this for trainig purposes. | SB1/D1/T1 | Take input form microphone. | GK+BB+MS
|  | SB1/D1/T2 | Converting the audio into appropriate format (Analog-to-digital converter). | GK+BB+MS
|  | SB1/D1/T3 | Converting the audio file into bit format. | GK+BB+MS
|  | SB1/D1/T4 | Collecting data into one file. | GK+BB+MS
SB1/US2 | As a devloper I want to classify the voices so that I can recognize the voice of human. | SB1/D2/T1 | Applying KNN. | GK+BB+MS
|  | SB1/D2/T2 | Applying K-Means. | GK+BB+MS
SB1/US3 | As a devloper I want to filter the voice of human so that I can reduce the noise. | SB1/D3/T1 | Detecting voice of any human being | GK+BB+MS
|  | SB1/D3/T2 | MFCC using Eigen values | GK+BB+MS
|  | SB1/D3/T3 | PLP-RASTA using Eigen values | GK+BB+MS
|  | SB1/D3/T4 | PLP using Fisher values | GK+BB+MS
|  | SB1/D3/T5 | Attribute Selection using Eigen values | GK+BB+MS
|  | SB1/D3/T6 | MFCC, PLP, PLP-RASTA | GK+BB+MS
|  | SB1/D3/T7 | MFCC using Fisher values | GK+BB+MS
SB1/US4 | As a devloper I want to classify the voice of male and female so that I can easily train the data accordingly | SB1/D4/T1 | Applying KNN. | GK+BB+MS
|  | SB1/D4/T2 | Applying K-Means. | GK+BB+MS
SB1/US5 | As a devloper I want to reduce the noise and perform data cleaning so that I can get the best result. | SB1/D5/T1 | Wavelet Transformation | GK+BB+MS
|  | SB1/D5/T2 | Attribute Selection using Eigen values | GK+BB+MS
|  | SB1/D5/T3 | Feature extraction for matching | GK+BB+MS
|  | SB1/D5/T4 | Attribute Selection using Fisher values | GK+BB+MS
SB1/US6 | As a devloper I want to train my system with different algorithm so that I can calculate the efficency and select the best model. | SB1/D6/T1 | Google-Speech-API | GK+BB+MS
|  | SB1/D6/T2 | Recognition of the Voice ( by recognizing use of frequency,modulation. ) | GK+BB+MS
|  | SB1/D6/T3 | Recognition of the voice (using Difffernt Algorithm) | GK+BB+MS
|  | SB1/D6/T4 | Recognition of voice (Using Differnet Algorithm) | GK+BB+MS
|  | SB1/D6/T5 | Google-Speech-API
SB1/US7 | As a devloper I want to apply the recognition algorithm so that I can get the output as text. | SB1/D7/T2 | Testing
|  | SB1/D7/T3 | Using it
|  | SB1/D7/T4 | Optimising it
|  | SB1/D7/T5 | Making it robust by time
SB1/US8 | As a devloper I want to convert the text input to speech so that machine can reply the anser accordingly as voice. | SB1/D8/T1 | Using windows own API.
|  | SB1/D8/T2 | Using Other API
|  | SB1/D8/T3 | Optimising it | GK+BB+MS
SB1/US9 | As a devloper I want to merge the speech to text and text to speech so that I can use it in my Application. | SB1/D9/T1 | Integrating both modules. | GK+BB+MS
|  | SB1/D9/T2 | Testing them.

## SB Hours 01
Sprint Backlog 1
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
1 | As a developer I want to develop the hardware so that Wii-mote can be placed on the screen | Search about the hardware setup
Search about components required
Purchase component from Market
Develop the hardware
2 | As a developer I want to search for applications to be developed so that I can identify an application to be developed | Search annotation application
search paint application
search video making application
search audio recording applications
3 | As a developer I want to study about the technology to be used so I can identify the technology for application | Study tutorials
Study tutorials
start with Basics of c#
start with Basics of c#
4 | As a developer I want to begin coding in swings so I can start with designing of the application | start with Basics of c#
start with Basics of c#
|  | coding of onscreen application |  |  |  | 0
|  | coding of onscreen application |  |  |  | 0
5 | As a developer I want to start coding of my application so that I can develop application | coding of onscreen application |  |  |  | 0
|  | coding of onscreen application |  |  |  | 0
Debug the code
Debug the code
6 | As a developer I want to implement my designed application so that I can use it | Implentation of application on virtual screen.
Implentation of application on virtual screen.
Implentation of application on virtual screen.
Implentation of application on virtual screen.
7 | As a developer I will implement the final project in the classrooms so that system can be used by the users at college | Switch on the projector and set the projected screen
Interface it with PC/laptop
Switch on the projector and set the projected screen
Interface it with PC/laptop
8 | As a tester I will check the whole system implemented in classrooms so that final system could be tested | Callibrate WII remote with virtual screen
Use different applications on the virtual screen
Check the changes made at the virtual screen
Checking if it is working effectively with the laptop and not damaged
9 | As a developer I will prepare the final delivarables of the whole system so that I can give the entire system | Prepare all hardware deliverables
Prepare all software deliverables
Prepare a hardware & software guide
Prepare a user manual & guide for the users
10 | As a developer I want to give training to faculty & students so that they can interact with the system & use it | Giving information to users about the project
Project demonstration
Project demonstration
Project to be operated by different users
| PG | Parth Gupta
| PK | Parv Khandelwal
| NG | Nicky Gupta
| PM | Pankaj Maheshwari
Verified By:
(Product Owner)

## SB BD Ch01
Spring Backlog 01 burn down chart
Date | Planned Total Task | Actual Incompleted Task
2018-09-04 | 33 | 180 | Tasks
2018-09-09 | 27 | 180
2018-09-13 | 20 | 180
2018-09-14 | 16 | 180
2018-09-16 | 10 | 180
2018-09-18 | 5 | 180
Days

## SprintBacklog 2
SPRINT BACKLOG 2
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 2 - <CHATBOT>
SB2/US1 | As a devloper I want to collect all the data from different converstations so that I can use them in my project as training data. | SB2/D1/T1 | Take input.
|  | SB2/D1/T2 | Convert it ino machine understandable.
SB2/US2 | As a devloper I want to filter and collect the data so that I can use it in my project. | SB2/D2/T1 | filter the input
|  | SB2/D2/T2 | apply various algorithms.
|  | SB2/D2/T3 | choose efficient algorithms
SB2/US3 | As a devloper I want to test different models so that I can get the sentiment of the input. | SB2/D3/T1 | test model.
|  | SB2/D3/T2 | choose efficient algorithms
|  | SB2/D3/T3 | sentiment analisys
SB2/US4 | As a devloper I want to test different models so that I can get the perfect output for the input. | SB2/D4/T1 | specifying output for different input.
|  | SB2/D4/T2 | appliying different model.
|  | SB2/D4/T3 | train the machine.
SB2/US5 | As a devloper I want to Select some best models so that I can use all of them in my chatbot | SB2/D5/T1 | testing
|  | SB2/D5/T2 | apply various algorithms.
|  | SB2/D5/T3 | select best model seeing efficient output.
SB2/US6 | As a devloper I want to calculate the confidence of different output from different model so that I can get the best output | SB2/D6/T1 | calculate confidence for different models.
|  | SB2/D6/T2 | select the best model with best confidence.
|  | SB2/D6/T3 | apply that model to get result.
SB2/US7 | As a devloper I want to make a adaptive algorithm so that chatbot can learn more through user past chat. | SB2/D7/T1 | train the system from past input of user.
|  | SB2/D7/T2 | optimize
SB2/US8 | As a Devloper I want to get interest of the user so that I can make it more user friendly | SB2/D8/T1 | get the interest from user.
|  | SB2/D8/T2 | user interest for selecting the model
|  | SB2/D8/T3 | get feedback from user.
SB2/US9 | As a User I want to use chatbot for getting Important reminders and information so that I can get the best out of it. | SB2/D9/T1 | give feedback.

## SB Hours 02
Sprint Backlog 2
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
| PG | Parth Gupta
| PK | Parv Khandelwal
| NG | Nicky Gupta
| PM | Pankaj Maheshwari
Verified By:
(Product Owner)

## SB BD Ch02
Spring Backlog 02 burn down chart
Date | Planned Total Task | Actual Uncompleted Task
2017-09-25 | 23 | 177 | Tasks
2017-09-28 | 16 | 177
2017-10-02 | 12 | 177
2017-10-05 | 9 | 177
2017-10-07 | 6 | 177
2017-10-09 | 3 | 177
0
Days

## SprintBacklog 3
SPRINT BACKLOG 3
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 3 - Virtual Assistant
SB3/US1 | As a Devloper I want to build the database so that I can save information of user in it. | SB3/D1/T1 | Devloping User Specific DataBase.
|  | SB3/D1/T2 | Connecting the assistant to Database.
SB3/US2 | As a Devloper I want to build the GUI of application so that It is more user friendly. | SB3/D2/T1 | Making GUI of the application.
|  | SB3/D2/T2 | Connecting the GUI with backend.
SB3/US3 | As a Devloper I want to add some features so that user can to Control my device through Assistant. | SB3/D3/T1 | Devloping the functanality of the application like opening window or differnet applications etc.
|  | SB3/D3/T2 | Devloping the functanality of the application for performing task like searching computer or calculating things etc.
|  | SB3/D3/T3 | Devloping the functanality to set reminders or other things
SB3/US4 | As a Devloper I want to add some web features so that user get all the information from various resourses in a single screen . | SB3/D4/T1 | Connecting the assistant to Internet.
|  | SB3/D4/T2 | Web Scrapping from media website like YouTube etc.
|  | SB3/D4/T3 | Web Scrapping from Socail Media website like Twitter, Facebook etc.
|  | SB3/D4/T4 | Web Scrapping from News Websites like TOI etc.
|  | SB3/D4/T5 | Web Scrapping from Information Website like Google/Wikipedia etc.
|  | SB3/D4/T6 | Web Scrapping from E-Commerce Websites.
SB3/US5 | As a Devloper I want to build the application more adaptive so that It can adapt itself according to user needs. | SB3/D5/T1 | Making the application adapting to the user.
|  | SB3/D5/T2 | Learning the interest area of user.
|  | SB3/D5/T3 | Leaning the voice model of user so efficency of speech Recognition will increase.
SB3/US6 | As a User I want to control other things with it so that It can save user time and energy. | SB3/D6/T1 | Connecting the assistant with other app like Calander/ Socail Media Account/ other application like Ola/Uber etc.
|  | SB3/D6/T2 | Building a secure way to save important information of User like password etc..
SB3/US7 | As a Devloper I want to intregate all Modules of project so that It can run smoothely. | SB3/D7/T2 | Integrating all modules of the project.
|  | SB3/D7/T3 | Connecting Chatbot with the Assistant.

## SB Hours 03
Sprint Backlog 3
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
| PG | Parth Gupta
| PK | Parv Khandelwal
| NG | Nicky Gupta
| PM | Pankaj Maheshwari
Verified By:
(Product Owner)

## SB BD Ch03
Spring backlog 3 Burnt Down chart
Date | Planned Total Task | Actual Uncompleted Task
2018-10-16 | 20 | 120 | Tasks
2018-10-18 | 15 | 120
2018-10-20 | 12 | 120
2018-10-21 | 7 | 120
2018-10-22 | 5 | 120
2018-10-23 | 3 | 120
0
Days

## SprintBacklog 4
SPRINT BACKLOG 4
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 4 - FINAL Testing
SB4/US1 | As a Devloper I want to optimize my application so that It work fast | SB4/D1/T1 | Optimization | GK
|  | SB4/D1/T2 | Testing | GK
SB4/US2 | As a Devloper I want to Implement my software on any platform so that I can get the live experience of it | SB4/D2/T2 | Implementing in the computer | GK
|  | SB4/D2/T2 | Track the accuracy and working | GK
SB4/US2 | As a devloper I want to test It again so that It doesnot give any errors in future | SB4/D3/T1 | Finding issues
|  | SB4/D3/T2 | Impleting again
|  | SB4/D3/T3 | Resolving issues
SB4/US4 | As a Devloper I want to devlop it for different platform and connect it with different applications so that It run indifferent environment. | SB4/D4/T1 | Connecting it with different applications
|  | SB4/D4/T2 | Check it on different Platforms

## SB Hours 04
Sprint Backlog 4
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
| PG | Parth Gupta
| PK | Parv Khandelwal
| NG | Nicky Gupta
| PM | Pankaj Maheshwari
Verified By:
(Product Owner)

## SB BD Ch04
Date | Planned Total Task | Actual Uncompleted Task
2019-01-10 | 9 | 190 | Tasks
2019-01-11 | 7 | 190
2019-01-12 | 6 | 190
2019-01-13 | 5 | 190
2019-01-14 | 3 | 190
2019-01-15 | 0 | 190
0
Days